## Slide 1: School Annual Leave Agreement (SALA) Briefing Slides Mary Jarrett, Director of Education Gurpreet Kataora, Head of School Business Support Zoe Henry, Programme Manager 4th September 2025 School Business Managers (SBM) Network

## Slide 2: Agenda
Introduction & Context Setting
Overview of New Processes:
  Process 1 – Current Staff in Progress
  Process 2 – Current Staff Not Started
  Process 3 – Leavers/Deceased
  Process 4 – Zero Hours
Next Steps

## Slide 3: Introduction & Context Setting
HR&OD were given 4 weeks notice on 22nd August 2025. LBWF will be delivering the remainder of the project.
There is a project team that will be supporting all schools to complete the process, including Gurpreet Kataora (Head of School Business Support) and Zoe Henry (Programme Manager).
We have created new processes to streamline the completion of the SALA project.
The deadline for schools that have started strands of work will be 1st November 2025 to ensure payments to employees are processed in 21st November 2025 payroll.
The deadline for schools that have not started all strands of work will be 1st December 2025 to ensure payments to employees are processed in 21st December 2025 payroll.
Action plans will be developed with each school to support achieving the above timelines.

## Slide 4: Outline
Strand 1 – TTO (Term Time Only Employees)
For the period of 5 years and 3 months commencing 1 January 2016 and ending 31 March 2021
Strand 2 – TTO NOPAL (Term Time Only Employees – Non-Payment of Average Annual Leave Payment)
The backpay for overtime represents the holiday pay that the Employee should have received for undertaken overtime during the period 1st April 2018 to 31st March 2022
Strand 3 – 52 Week & Teacher NOPAL
As above for those on 52 week contracts & teachers
The existing strands will be embedded into 3 new processes:
Process 1 = Current Staff in Progress
Process 2 = Current Strands Not Started
Process 3 = Leavers/Deceased
Strand 4 – Zero Hours
LBWF Casual worker AL entitlement
Carlene (WF) will work with schools on implementing the correct calculation

## Slide 5: Process 1: Current Staff In Progress
SBM to send copy of SPOT to WF via secure email with password protection
By 08/09
School 1:1s
SBM, HT & EBE Team to attend a 1:1 meeting to discuss completion rate, any barriers & action plan. EBE team to arrange.
8/09/25 – 19/09/25
WF Create Letter Templates for Schools
Outlining the new timelines and actions to complete Uploaded to The Hub and sent directly to SBMs via TTO email
w/c 08/09/25
ACAS Webinar
SBM to arrange webinars for remaining staff:
In person session in school and/or
Staff to complete in their own time
Completed by 25/09/25
COT3 Signed Schools to arrange paper forms to be handed to staff and staff are given 14 days to sign
10/10/25
SBMs to confirm staff lists who’ve signed off COT3
By 17/10/25
Payments for November Payroll
Completed
Weekly Drop In Sessions
WF Project Team
Opportunity to ask questions and identify any risks
Weekly FAQs will be distributed to schools
TBC
Letters to be sent to all staff by SBMs inviting them to attend ACAS Sessions
ZH will coordinate with Education Finance to ensure payments are processed to schools

## Slide 6: Process 2: Certain Strands Not Started
1:1 with Schools
SBM & EBE Team to work through current status across all strands, barriers and action plan
Data
WF to send a template to SBM to send data required to WF
(All Strands)
Send by secure email and password protected
By 29/09/25
SPOT
WF to send SPOT to HT for Sign Off
From Receipt from School
2-week process
Letters to all staff Offer Letter & COT3 Process
Outlining the new timelines and actions to complete
By 20/10/25
ACAS Webinar
SBM to arrange webinars for remaining staff:
In person session in school and/or
Staff to complete in their own time
24/10/25
COT3 Signed Schools to arrange paper forms to be handed to staff and staff are given 14 days to sign
By 10/11/25
SBM to confirm COT3 Signed
By 17/11/25
Payments for December Payroll
Completed
Fortnightly Check Ins – EBE Team & SBM on Progress
ZH will coordinate with Education Finance to ensure payments are processed to school

## Slide 7: Process 3: Leavers/Deceased/RAG Red
This will be a separate process and will be discussed during 1:1s with each school and an action plan will be created.

## Slide 8: Next Steps
LBWF Actions:
1:1s will be scheduled for all SBM with EBE team – Commencing 08/09 – 19/09
Template for SPOT submission will be sent by 08/09/25
Letter templates for staff will be sent w/c 08/09/25
Templates will be uploaded to the Hub w/c 08/09/25
Weekly drop in sessions to be scheduled from 19/09/25 onwards
Process 2 fortnightly update meetings will be scheduled with Project Team.
A FAQs document will be sent to SBMs following this meeting.
SBM Actions:
SBMs to arrange ACAS sessions for Current Staff
Send required information:
  Process 1: Send Copy of SPOT by 08/09
  Process 2: Data sent by 29/09
  Details of employees who have signed COT3s
If you have any further queries/questions, please email the Project Team at: Termtimeonly.Payments@walthamforest.gov.uk

## Slide 9: Thank you