## Slide 1: Redundancy Process - Guide for Schools
29 September 2026

## Slide 2: Introduction
Carlene Reid – Senior Business Partner Schools HR
Donna Carby – Senior Business Partner Schools HR
Gurpreet Kataora – Head of School Business Support
Pamela Stack – Finance Business Partner - Education

## Slide 3: Preliminary Stage
Is there a financial shortfall?
Many factors can influence the financial health of your school, such as
Falling rolls
Unfunded pay increases
Withdrawal of funding
Unplanned emergencies

## Slide 4: Preliminary Stage
Identify that there is a problem.
Staffing is the single biggest cost for a school.
Suspend all but essential permanent recruitment
Notify the governors that you will have to be looking at potential staff restructuring to balance the budget.
You may wish to contact the unions to give them the heads up!
At this stage governors may select a panel of governors to lead on the restructure to support the school’s leadership team.

## Slide 5: Stage One – 2 weeks
The Head, SBM and Chair of Governing Body to meet with HR support, Finance and School Improvement Partner to discuss:
  Process and Policy guidance.
  Provide templates such as model job descriptions and financial modelling.
  General guidance incl. VR
  Service delivery and design.

## Slide 6: Stage Two – 3 weeks
School to draft a business proposal using the templates including:
Financials – before and after identifying the full year effect.
Before and after staff structure charts.
Provide equality impact assessment and workload impact assessment.
Job evaluation;
Provisional Pension strain costs.
Provisional Safeguarded costs and timelines.
Provisional Redundancy costings.
Schools HR and School Finance can provide support with this stage

## Slide 7: Stage Three and Four – 2 weeks
Stage three – 1 week
Draft restructure proposal to be sent to:
  Schools HR,
  Director of Education, and
  Education Finance
for final compliance check to enable provisional approval for redundancy reimbursement.
Education Finance to inform schools of outcome within 1 week.
Stage four – 1 week
Head Teacher and Governors to present to Redundancy panel for final sign off (subject to any changes).
Arrange an extraordinary meeting with Governors to agree in principle the proposals..

## Slide 8: Stage Five – 1 week
The draft proposal should be complete and include:
The business rationale
A timeline that is clear, with dates, up to your implementation date.
An Equalities Impact Assessment
A workload Assessment
New Job Descriptions
Current and Proposed staffing structure
Financial information
Governors to approve in principle the draft proposal document. (THIS MAY REQUIRE AN EXTRAORDINARY GOVERNORS MEETING)
As soon as governors agree in principle the document to be sent to all relevant trade unions with a date for formal consultation to start the following week. Trade unions to be invited to the meeting.

## Slide 9: Stage Six – 6 to 8 weeks
Formal consultation to commence for 30 working days (not including school closures).
Initial meeting with Trade Unions and staff to mark the start of consultation.
During consultation offer individual consultation meetings.
Staff can request VR during the consultation period.
All staff, not just those affected, encouraged to engage with the consultation.
All feedback to be shared with the panel of governors for consideration
Final ratification

## Slide 10: Stage Eight – 2 weeks
1. Selection processes:
Issue letters of assimilation
Ring-fenced interviews
Redundancy Notices issued (community schools to get final dismissal letter sent by the LA) notify pensions
External recruitment can begin.
2. Appeals
3. Implementaton
Individuals can appeal against their redundancy dismissal within 10 working days of receipt of the letter.